## Backlog
Module | US | Desc | Dependancy | Risk | Owner | Status | Comment
Database info | 1 | As a 3pp system, I can get the database name | Database type confirmation |  | wpm | on going
| 2 | As a 3pp system, I can get the database type | Database type confirmation |  | wj | on going

## Cardwall
Sprint1
US | Desc | Tasks | Assign to | Estimate points
1 | As a 3pp system, I can get the database name | 1 mybatis config | wpm | 1
|  | 2 java code | wpm | 1
|  | 3 test | wj | 1

## Schedule
Sprint | Start | End
1 | 2018-02-26 | 2018-03-11
2 | 2018-03-12 | 2018-03-25

## 注释
编号 | 表头 | 解释 | 子项
1 | Module | 所属大模块
2 | US | User story
3 | Dependancy | 依赖块，例如，需要查询某库表，那么必须先有这个库表
4 | Risk | 风险分析
5 | Owner | 负责人
6 | Assign to | 具体开发人员
7 | Status | 状态 | 1. Blocking 2. On going 3. Reviewing 4. Closed 5. Done
8 | Comment | 注释
9 | Estimate points | 工作量, 按一人天计算，例如这个task 评估2，那么就是一个人2天的工作量